## 1. Test Strategy
Test Strategy — Scratchcard "Schatzsuche" (Treasure Hunt)
Objective | Make sure every ticket the Schatzsuche generator produces actually follows the 15 rules in the spec, and that the full population lines up with the declared prize plan i.e.,1,830,000 tickets, 183,000 free tickets, 1:7.12 odds of any prize, 1:915,000 for the top prize. The approach throughout is to take the rules as ground truth and run every ticket (or a statistically sound sample) against them, producing a clear result per rule: the population either contradicts that rule — a defect, with the offending ticket IDs as evidence — or it doesn't. A UI glitch here is annoying; a wrong payout, a rule violation that quietly shifts the odds, or a ticket batch that drifts from the certified plan is a different category of problem, with regulatory exposure attached.
Scope — In | Rule-by-rule checks (Rules 1-15) on individual tickets, plus statistical validation across the full population against the prize plan. Covers the Winning Class to payout mapping, DOPPLER doubling, when FREILOS gets issued, book-level sequencing (no repeats, no long dry runs), the 6-win cap, and the area most likely to hide a real issue is every combination of WINNER/DOPPLER/FREILOS/amount a ticket could show, valid and invalid, on both winning and non-winning tickets.
Scope — Out | Payment processing, how the scratch animation itself renders(if present), certifying that the random draw behind ticket allocation is truly fair (assumed to sit with an independent auditor — see the risk list), UI translation, and regulator-specific report formats. These are called out as risks/assumptions rather than tested directly, since none of them were part of the material provided.
Manual vs. Automated | Manual has a real place early on: reading the 15 rules for contradictions before writing a single test, and later spot-checking that the client actually renders what the backend says. But the core of this plan — checking 1,830,000 tickets against 15 rules — isn't something manual sampling can do reliably. A manual validation of a few hundred tickets by hand will simply never encounter the 2 WC10 tickets, or the rare invalid symbol combination that only shows up once in ten thousand draws. So the rule checks are written to be automated from the start, and manual effort is reserved for the things automation genuinely can't do (does it look right, does it feel right) rather than spread thin across everything.
Automation Scope — Local, Not CI | Worth being explicit about this: these checks are batch data-validation, not a CI/CD test suite. Ticket generation isn't continuous deployment — a new print run happens when a new batch is generated, not on every code commit — so wiring these checks into a pipeline that runs on every push doesn't match how the thing actually gets produced. The natural home for this automation is a local/offline validation pass a QA engineer (or a scheduled job) runs against each new ticket export before it's signed off for print, not a gate that blocks a deploy. If the generator logic itself later moves into a CI-tested codebase, unit tests on that logic belong in CI — but validating the actual ticket output against the certified prize plan stays a separate, on-demand check against real generated data.
Test Design Techniques | Equivalence partitioning across winning classes and win-count buckets (0 / 1-5 / 6). Boundary value analysis at the edges that actually matter — 5 vs 6 wins, 9 vs 10 consecutive non-winners, the 2nd/915,000th top-prize ticket. The technique doing the most work here, though, is a decision table over every WINNER/DOPPLER/FREILOS/amount combination (see the Symbol Combination Matrix tab) — because a ticket's win status, its symbols, and its displayed amount are supposed to be one linked outcome, but if the generator rolls them somewhat independently, rare draws can produce combinations that shouldn't be possible: a WINNER symbol sitting next to €0, an amount displayed with no WINNER anywhere on the ticket, FREILOS without an actual free-ticket win. None of these show up in a quick manual sample — they're exactly the kind of thing that only surfaces once you scan the full population against every cell of the matrix, valid and invalid alike. Alongside that: negative tests for every 'must not appear' rule, and rather than try to enumerate 1.83M tickets, a statistical check comparing how many tickets actually landed in each class against how many the prize plan says should have, run at more than one sample size so a fluke at one sample doesn't get mistaken for a real problem.
Test Environment / Data | Best case: a full or sampled export of generated tickets from a staging build, checked with a local validation pass (see Automation Scope above). If that doesn't exist yet, ask the ticket-generator team for at least a 50,000-ticket sample — small samples won't reliably contain the rarer classes (WC9, WC10 only have 10 and 2 tickets total in the whole plan), so anything smaller makes the statistics, and the odds of catching a rare invalid combination, unreliable.
Entry Criteria | Prize plan and the 15 rules are locked, or any open ambiguity has been explicitly signed off by the product owner rather than left for QA to guess. A ticket export or generator API exists somewhere QA can reach it.
Exit Criteria | Zero rule violations across the full population, or across a sample large enough to be statistically meaningful — meaning every check comes back non-contradicting, not just the common cases. Observed winning-class frequencies within the agreed confidence interval of the declared plan. Every cell of the Symbol Combination Matrix marked invalid has zero real tickets in it. All High-priority cases below pass.
Reporting | Every check in this plan is built to return one of two states against a specific rule: the ticket population contradicts it (a defect, logged with the rule, the offending ticket ID(s), expected vs. actual, and severity) or it doesn't. Statistical findings get reported with the actual counts and how far off they are from what's expected, not just a raw mismatch — a count being off by itself doesn't tell anyone whether that's a real bug or normal sampling noise.

## 2. Risk Assessment
Risk | Likelihood | Impact | Why it matters | Mitigation / Test Case
Random generation treats linked attributes independently | Medium | High | Win status, symbols (WINNER/DOPPLER/FREILOS), and displayed amount are supposed to be one linked outcome per ticket. If the generator rolls them as separate independent random draws instead of deriving them all from a single outcome, rare combinations that shouldn't exist — a WINNER symbol next to €0, an amount shown with no WINNER anywhere on the ticket — can slip through purely by chance. A manual sample of even a few thousand tickets is unlikely to ever hit one. | Full decision-table scan of every symbol/amount combination across the whole population — see the Symbol Combination Matrix tab — rather than spot-checking a handful of 'normal-looking' tickets.
Wrong payout on a winning ticket | Low | Critical | There are roughly 257,000 winning tickets in this print run. Even a one-in-a-million bug in the WC-to-prize mapping pays out the wrong amount across a chunk of them before anyone notices. | Full-population check of the WC-to-prize mapping (TC-01/02) and the DOPPLER doubling logic (TC-22).
Ticket population drifts from the certified odds | Medium | Critical | 1:7.12 and 1:915,000 aren't marketing numbers — they're what's certified to the regulator. A generation bug that skews the distribution is a compliance breach, not a cosmetic issue. | A statistical distribution check at more than one sample size (TC-04 to TC-06).
A win symbol shows up where it shouldn't (Rules 11, 13-15) | Medium | High | These symbols are the entire signal a player uses to know they won. Leaking WINNER/DOPPLER/FREILOS onto a losing ticket effectively promises a prize that never gets paid — or the reverse. | Negative and decision-table checks, TC-23 and TC-25 to TC-27.
Ticket-book sequencing breaks down (Rules 6, 8) | Medium | Medium | A repeated layout on back-to-back tickets, or a long stretch with nothing winning, is the kind of pattern a suspicious player (or a regulator's own audit) would notice. | Scan each printed book as a sequence, not just ticket-by-ticket (TC-16, TC-18 to TC-19).
Free-ticket (FREILOS) count or placement is off | Medium | High | 183,000 free tickets are supposed to spread across multiple winning classes and only ever accompany a real free-ticket win. Get this wrong and the effective prize plan is different from the declared one even though nothing on paper changed. | Population-level count check plus per-ticket FREILOS linkage (TC-09 to TC-10).
The random number generator behind ticket allocation isn't independently certified | Low | Critical | Out of scope for this plan, but worth naming: if which ticket gets which prize is decided by an in-house random number generator without third-party certification, the distribution check below only catches gross bias — not the subtle kind a real certification process is designed to rule out. | The distribution check (TC-06) gives an early signal if something's badly wrong, but it's not a substitute for certification — request that evidence from whoever owns the random number generator before sign-off.
Client display disagrees with the backend | Low | High | A correct backend doesn't help if the client shows the wrong number. | Spot-check the client against the raw payload for at least one ticket per winning class (TC-28 to TC-30).

## 3. Symbol Combination Matrix
Symbol Combination Matrix (every state a ticket's win-flag, symbols, and amount could be in)
Note: A ticket's winning class, its WINNER/DOPPLER/FREILOS symbols, and its displayed amount aren't independent facts — they're one outcome. This table enumerates the combinations that outcome can validly take, and just as importantly, the ones it can't. The 'invalid' rows are the ones worth automating a scan for: they're rare by definition, so a manual sample is unlikely to ever land on one, but a generator bug that rolls these attributes independently instead of jointly can still produce them.
Winning? | WINNER | DOPPLER | FREILOS | Amount | Valid? | Why | Rule(s)
No | Absent | Absent | Absent | Decorative only (never payable) | Valid | The baseline non-winning ticket. Any euro-amount graphic present is a pure decoy per Rule 4. | Rules 3, 4, 12
No | Present | Any | Any | Any | Invalid | A non-winning ticket must never show WINNER — that's the entire signal a player uses to know they won. | Rule 13
No | Any | Present | Any | Any | Invalid | DOPPLER on a non-winning ticket implies a doubled win that doesn't exist. | Rule 14
No | Any | Any | Present | Any | Invalid | FREILOS on a non-winning ticket promises a free-ticket prize that isn't real. | Rule 15
Yes (ordinary win) | Present | Absent | Absent | > €0, matches class | Valid | The standard case — WINNER marks the win, the amount shown is exactly the class payout. | Rule 9
Yes (ordinary win) | Present | Absent | Absent | €0 | Invalid | A winning ticket that pays nothing and isn't a free-ticket win is a contradiction — it claims a win with no prize attached. | Rules 9, 10, prize table
Yes | Absent | Any | Any | Any | Invalid | Any real win — doubled or not — still needs WINNER present. A winning ticket with no WINNER symbol anywhere is a broken ticket, not just an unusual one. | Rule 9
Yes (DOPPLER win) | Present | Present | Absent | Exactly 2x the pre-double amount, doubled result matches a real class | Valid | DOPPLER doubles the shown amount to reach the paid class — holds at every level including the top prize (€7,500 shown → €15,000 paid). | Rule 10
Yes (DOPPLER win) | Present | Present | Absent | Doubled result doesn't match the paid class | Invalid | The doubling math is broken — the ticket pays an amount that doesn't correspond to exactly double what was shown before reveal. | Rule 10
Yes (free-ticket win) | Present | Absent | Present | N/A (prize is a ticket, not a euro amount) | Valid | The free-ticket case — WINNER plus FREILOS together, no monetary amount to check. | Rules 2, 9, 11
Yes (free-ticket win) | Present | Present | Present | N/A | Invalid (by design assumption) | A ticket prize being doubled doesn't make sense — DOPPLER doubles a monetary amount, and a free ticket isn't one. Flagging this combination as something that should never occur in the data, not just visually odd. | Rules 2, 10, 11
Any | Absent | Any | Present | Any | Invalid | FREILOS must never appear without WINNER alongside it, regardless of anything else on the ticket. | Rule 11
Any | Any | Any | Present | Any (but the ticket didn't actually win a free ticket) | Invalid | FREILOS is showing on a ticket that didn't actually win a free ticket — the display and the real outcome have come apart. | Rule 2

## 4. Test Cases
ID | Category | Rule(s) Ref. | Title | Test Data | Steps / Approach | Expected Result | Priority | Type (if applicable)
TC-01 | Prize Plan Mapping | Prize table | Winning class pays the fixed amount it's supposed to | One real ticket per class, e.g.: WC1/€4, WC3/€10, WC6/€40, WC9/€1,000, WC10/€15,000 (the mapping is: WC0=€0, WC1=€4, WC2=€8, WC3=€10, WC4=€20, WC5=€25, WC6=€40, WC7=€50, WC8=€100, WC9=€1,000, WC10=€15,000). | Pull the winning class and paid amount for each sample ticket from the export; compare the paid amount to the table value for that class. | The paid amount matches the table exactly for every sampled ticket, e.g. the WC3 ticket pays €10, not €8 or €12. | High | Automated
TC-02 | Prize Plan Mapping | Prize table | Class counts match the declared distribution | Full export of 1,830,000 rows, or a 500,000-row sample for a proportional check. | Group tickets by winning class and compare the counts against the declared table (WC10=2, WC9=10, WC8=1,069, WC7=1,500, WC6=1,300, WC5=500, WC4=4,800, WC3=54,000, WC2=32,900, WC1=161,100, WC0=1,572,819). | Every count matches exactly on a full-population export (e.g. WC8 count is exactly 1,069, not 1,068 or 1,070). On a sample, each count sits within the confidence interval from TC-06. | High | Automated
TC-03 | Prize Plan Mapping | Prize Plan Statement | Ticket count is 1,830,000 | The full export. | A row count against the ticket export or database table. | 1,830,000 rows. The 183,000 free tickets are treated as a subset of this population — a ticket's prize can itself be another ticket — rather than an addition to the print run, consistent with Note 2's wording that they 'can occur in any winning class.' | Medium | Automated
TC-04 | Statistical Validation | Odds statement | Overall odds come out to 1:7.12 | Full export: 1,830,000 tickets, 257,181 of them winning (any WC1-10). | 1,830,000 / 257,181. |  | High | Automated
TC-05 | Statistical Validation | Odds statement | Top prize odds come out to 1:915,000 | Full export: 1,830,000 tickets, 2 of them WC10. | 1,830,000 / 2. | Exactly 915,000. | High | Automated
TC-06 | Statistical Validation | Prize table | Distribution holds up at different sample sizes | Random samples of 50,000 and 500,000 tickets pulled from the staging generator (not from the full population export, to simulate what a real pre-launch QA cycle would actually have access to). | Run a statistical test that compares how many tickets actually landed in each class against how many should have, at both sample sizes, and reports whether the gap is bigger than normal random variation would explain. | The gap stays within normal random variation at both sample sizes. If the test instead says a sample's results are too far off to be chance, that's a signal to investigate the generator, not to rerun the sample and hope for a better draw. | High | Automated
TC-07 | Rule Compliance | Rule 1 | €15,000 field is shown on every ticket with 1-5 wins | Ticket #A: 1 win (a single €4 prize). Ticket #B: 3 wins (an €8 + €20 + €50 combination). Ticket #C: 5 wins. None of these actually land on WC10 — the €15,000 field is a fixed display element, independent of what the ticket actually pays. | Check whether the top-prize field is shown on each. | Present on all three, regardless of what they actually won. | High | Automated
TC-08 | Rule Compliance | Rule 1 | €15,000 field is the one thing missing on a 6-win ticket | Ticket #D: 6 individual wins (e.g. six separate small prizes filling every slot on the card). | Check whether the top-prize field is shown. | Absent — the field isn't printed on 6-win tickets, presumably because there's no layout space left once all 6 win slots are used. Everything else about the ticket (the 6 real wins) is otherwise unaffected. | High | Automated
TC-09 | Rule Compliance | Rule 2 / Note 2 | FREILOS only shows up on a real free-ticket win | Ticket #E: WC2 winner, paid €8, no free-ticket win attached. | Check for the FREILOS symbol on tickets that didn't actually win a free ticket. | Absent on ticket #E and every other ticket like it. | High | Automated
TC-10 | Rule Compliance | Note 2 | Free-ticket count and spread across classes | Full export. | Count tickets flagged as free-ticket wins; group those by winning class. | 183,000 total, and spread across more than one winning class (e.g. not all 183,000 sitting inside WC1). | Medium | Automated
TC-11 | Rule Compliance | Rule 3 | Decorative symbols are roughly evenly spread | Full export, the 12 non-prize symbols: BRILLE, MOEWE, SEETANG, OKTOPUS, SEESTERN, HAI, SCHLOSS, SCHIFF, MUSCHEL, KOMPASS, KARTE, DREIZACK. | For each symbol, count occurrences on winning vs. non-winning tickets, normalise by population size of each group. | No symbol's rate on winning tickets is wildly different from its rate on non-winning tickets, beyond what Rules 1/2/5-11 already force it to be. | Low | Automated
TC-12 | Rule Compliance | Rule 4 | Amounts shown on a non-winning ticket never actually trigger a payout | Ticket #F: non-winning, but shows a €20 amount graphic in one of its fields — this is expected under Rule 3 (amounts get distributed across both winning and non-winning tickets so a player can't tell from symbol variety alone which is which). Rule 4 is the constraint that keeps that safe: the decoy amount is never wired to an actual payout. | Attempt to reveal/settle ticket #F through the normal game flow; confirm no payout occurs off that decoy field. | Ticket #F settles at €0 despite showing a €20 graphic. | Medium | Manual
TC-13 | Rule Compliance | Rule 3 / 4 | Decorative and prize-triggering amount fields can't be confused with each other | Ticket #F (non-winning, decorative €20 graphic per above) and Ticket #B (an actual WC4 win, real €20 payout) both display the same-looking €20 symbol. | Check that the two fields are structurally distinct in the underlying data (e.g. a decorative-field flag vs. a payout field) rather than relying on visual similarity alone to keep them apart. | The game engine can never mistake ticket #F's decoy €20 for a real win, even though it looks identical to ticket #B's real €20 to the player. This is the edge case Rule 3's 'evenly distributed' requirement opens up, and Rule 4 is what closes it. | Medium | Manual
TC-14 | Boundary / Negative | Rule 5 | 6 wins on one ticket is a valid, supported state | Ticket #G: 6 individual wins, e.g. 2x€4 + €8 + €10 + €20 + €25. | Confirm the ticket is accepted/settles normally, and that Rule 1 (no €15,000 field) and Rule 7 (repeat amounts allowed when justified — here the €4 appears twice) both hold for it. | Ticket #G settles correctly; no €15,000 field; the duplicated €4 is fine since two real wins justify it. | High | Automated
TC-15 | Boundary / Negative | Rule 5 | No ticket ever exceeds 6 wins | Full export. | Filter for any ticket with more than 6 individual wins. | Zero rows. Any hit here is a Critical defect — it means the real odds are different from the certified prize plan. | High | Automated
TC-16 | Ticket Book Rules | Rule 6 | No two tickets in a row within a book are identical | Book #B-014, 40 tickets in print order (position 1-40). | Walk the book from position 1 to 40, comparing each ticket's full layout (class, win count, symbol set) against the one right after it. | No two adjacent positions in book B-014 (or any other book) share the same layout. | Medium | Automated
TC-17 | Rule Compliance | Rule 7 | A prize amount doesn't repeat on a ticket unless a second win actually justifies it | Ticket #H: single €10 win, amount shown once. Ticket #I: two separate €10 wins (2 individual wins), amount legitimately shown twice. | Count occurrences of each prize amount on the ticket; cross-check against win_count. | Ticket #H shows €10 exactly once. Ticket #I shows €10 exactly twice, matching its two real wins. | Medium | Automated
TC-18 | Boundary / Negative | Rule 8 | Exactly 9 consecutive non-winners is fine | Book #B-021, positions 5-13 are all non-winning (9 in a row), position 14 is a winner. | Walk the book counting the longest run of non-winning tickets (free tickets count as winning). | The run of 9 at positions 5-13 is accepted; position 14 breaks it as expected. | Medium | Automated
TC-19 | Boundary / Negative | Rule 8 | No run of 10+ non-winners ever happens | Full export, every book. | Same walk as above, flag any run >= 10. | Zero occurrences across every book. Even one instance is High severity — it's a pattern a suspicious player or a regulator's own audit could pick up on. | High | Automated
TC-20 | Combinatorial | Rules 2/9/10/11/13-15 | No ticket anywhere in the population falls into an invalid cell of the Symbol Combination Matrix | The full export. This is the consolidated version of the individual symbol-negative tests below — one scan against every 'Invalid' row in the matrix (see the Symbol Combination Matrix tab) instead of treating each as a separate one-off check. | For every ticket, derive its (winning?, WINNER, DOPPLER, FREILOS, amount) tuple and look it up against the matrix. Flag any ticket landing in a row marked Invalid. | Zero matches against any invalid row. This is the primary defense against the specific risk that matters most here: a generator that rolls these attributes independently instead of deriving them from one outcome, which would produce exactly this kind of rare, otherwise-easy-to-miss combination. | High | Automated
TC-21 | Rule Compliance | Rule 9 | WINNER marks every non-DOPPLER win; FREILOS is the special case, not the default | Ticket #J: WC4 winner (€20), ordinary win, no DOPPLER. Ticket #N: a free-ticket win, also no DOPPLER — same WINNER symbol, but the field next to it shows FREILOS instead of a euro amount, because this particular win happens to be a free ticket (Rule 2's condition). | Check that WINNER is present on both tickets #J and #N; check that FREILOS is present only on #N, not on #J. | WINNER on both. FREILOS only on #N. This reads Rule 9 as: WINNER is the marker for any win that didn't come via DOPPLER, and what sits next to it is either the amount or, specifically for a free-ticket outcome, FREILOS — consistent with Rule 2 (FREILOS only on real free-ticket wins) and Rule 11 (FREILOS always with WINNER). | High | Automated
TC-22 | Rule Compliance | Rule 10 | DOPPLER always shows exactly half the final prize, doubling it on reveal — no exception for the top prize | Ticket #K: final class WC7 (€50) via DOPPLER — the field next to DOPPLER shows €25 before reveal. Ticket #P: the rare case of a WC10 win (€15,000) also won via DOPPLER — the field next to DOPPLER shows €7,500 before reveal. | Check that the amount shown adjacent to DOPPLER, before the doubled result is applied, equals exactly half the final paid amount — for every DOPPLER win in the export, including the WC10 case if one exists. | Holds exactly in both cases: €25 doubles to €50, €7,500 doubles to €15,000. DOPPLER behaves the same way at every prize level, with no special-cased exception at the top. | High | Automated
TC-23 | Rule Compliance | Rule 11 | FREILOS never shows up without WINNER alongside it | Ticket #L: a real free-ticket win, showing the FREILOS symbol. | Check whether WINNER is also present on ticket #L and every other ticket showing FREILOS. | Present on all of them — FREILOS and WINNER always appear together. | High | Automated
TC-24 | Rule Compliance | Rule 12 | Non-winning tickets have no duplicate symbols | Ticket #M: non-winning, showing BRILLE, MOEWE, SEETANG, OKTOPUS, SEESTERN, HAI. | List ticket #M's symbols, check for repeats. | All 6 symbols on ticket #M are distinct — same check across every non-winning ticket in the export. | Medium | Automated
TC-25 | Negative | Rule 13 | WINNER never appears on a non-winning ticket | Every non-winning ticket in the export. | Check for the WINNER (GEWINNER) symbol on each. | Absent on all of them. Any hit here is Critical — a player would reasonably believe they'd won. | High | Automated
TC-26 | Negative | Rule 14 | DOPPLER never appears on a non-winning ticket | Every non-winning ticket in the export. | Check for the DOPPLER symbol on each. | Absent on all of them. | High | Automated
TC-27 | Negative | Rule 15 | FREILOS never appears on a non-winning ticket | Every non-winning ticket in the export. | Check for the FREILOS symbol on each. | Absent on all of them. | High | Automated
TC-28 | UI / Client Consistency | General | Client display matches the backend payload, one ticket per class | 10 real tickets pulled from staging, one per WC1-WC10. | Reveal each ticket in the client (mobile emulation); pull that same ticket's payload from the backend/API; compare amount shown, symbol layout, and free-ticket flag. | All 10 match exactly between client and payload. | High | Manual
TC-29 | UI / Client Consistency | General | A losing ticket renders with no win indicators at all | 1 confirmed non-winning ticket. | Reveal it in the client. | No win animation, no amount shown, no free-ticket indicator; balance display doesn't move. | Medium | Manual
TC-30 | UI / Client Consistency | General | Client-side tampering can't change the outcome | Any ticket, revealed via the normal game flow with browser dev tools open on the reveal request. | Intercept the reveal request and try editing the response/client state before the result is committed on screen. | The outcome shown doesn't change — it was already locked server-side before the request came back. | High | Manual